## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone | 2022-03-11 | 2022-07-11 | 2022-08-11 | 2022-11-11
Features in scope | GTSFR API | Dublin Bus SQL | Dublin Bus Stops Page | Search Dublin Bus Stops
Features implemented | GTSFR API | Dublin Bus SQL | Dublin Bus Stops Page | Search Dublin Bus Stops
Features in deficit this Iteration | Serializing Data | Remaining tables for database | Google Maps | Results Dropdown Search Bar
Iteration Comments & Summary | I was able to get into the API into the Databse however it crashes as it can only take so much requests, will need to find a fix for next iteration | I was able to fix the accuracy of data and is now fit for accurate usage | I was able to successfully add the Stops Page to display the bus times information.The Page however is missing the Google Maps API, which will be added on later | I was able to successfully add the Search functionality for dublin bus stops, however I will need to be able to showcase the search results on the search bar rather than redirecting the user to a new page with search results | .
Iteration #2
Date of milestone | 11/18/2022 | 11/27/2022 | 11/31/2022 | 2022-03-12
Features in scope | GTSFR API | Stop Times Accuracy | Google Maps API | User Login, SignUp and Logout
| GTSFR API | Stop Times Accuracy | Google Maps API | User Login, SignUp and Logout
Features in deficit this Iteration | Serializing Data | Categorising Service Days | Google Maps API Access Key | User Edit Profile, Edit Password
Iteration Comments & Summary | I was able to get into the API into the Databse however it crashes as it can only take so much requests, will need to find a fix for next iteration | I was able to fix the accuracy of data and is now fit for accurate usage | Still need to get access for the API key of google maps in order to show users the stop location on map | Successfully added accounts to be created and stored into database, however needs more features for the user to be able to use | .
Iteration #3
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #5
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #6
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary